## Sheet1
Process Name | Interfaces | Effort Estimation | Details
Ereq_Master_Data_Synchronisation | Putty, CMD, Sharepoint, API call, Database server, SMTP server | Automation not required | Robot will extract project code data from Putty and compare it with the SharePoint list. If data is new, it will enter new data into SharePoint using an API call.
Ereq_QAD_Integration(PO Creation) | Putty, Sharepoint, API call, Database server, SMTP server, Utility | Optional(2 weeks) | Robot will read data from Sharepoint and enter it into the utility application for the creation of a request ID in the Sharepoint list. Robot will read Sharepoint PO creation list with status "Ready for Creation" and extract all EREQ details and enter them into Putty for PO creation. Once it is done, the robot will update the PO number and date in the SharePoint list and update the database. In case of failure, it will update the EREQs with a PO not generated status and drop mail to the SharePoint team with a failure reason and update the database.
On Time Delivery Continued | Putty, 32prn, FTP Server, ODS folder, Excel, SMTP Server | 8 | Robot will extract the report from Putty and forward it to the ODS folder using FTP Server.
GL_Calendar_Opening | Putty, SMTP server | Automation not required | Robot will enter data on a monthly basis into Putty and drop mail to the QAD Team.
Monthly_ODS folder_Balancesheet_Process | SAP, Excel, FTP Server, ODS folder folder, Smtp server | 0 (No Change Required) | Robot will extract the report from SAP and forward it to the ODS folder using FTP Server.
Monthly_QAD_Download_report | Putty, 32prn, FTP Server, ODS folder, Excel, Smtp server | 4 | Robot will extract the reports from Putty and forward it to the ODS folder using FTP Server.
ODS_Autocrib_Automation | Autocrib site, Web beowser(Chrome), UI Interfaces, Excel, FTP server, ODS folder, SMTP Server | 0 (No Change Required) | Robot will extract report from autocrib site and forward it to FTP server.
ODS_TG1_BalanceSheet | SAP, Excel, FTP Server, ODS folder folder, Smtp server | 0 (No Change Required) | Robot will extract the reports from SAP and forward it to the ODS folder using FTP Server.
Open_Asn_Report | Putty, 32prn, FTP Server, ODS folder, Excel, SMTP Server | 8 | Robot will extract reports from Putty, filter the data in Excel, and highlight cells with different colors according to business requirements. Robot sends an Excel with colored cell information into mail to the client and forwards it to the FTP server.
QAD_Customer_Forecast_Dashboard | Putty, 32prn, FTP Server, ODS folder, Excel, SMTP Server | 6 | Robot will extract the report from Putty and forward it to the ODS folder using FTP Server.
QAD_Customer_Invoice_Automation | Putty, 32prn, Excel, PDF, SMTP Server | 12 | Robot will extract the invoice data in Excel from Putty, make some filters and read invoice details, extract invoices from Putty using invoice number, and send invoices to different customers.
QAD_Download_File | Putty, 32prn, FTP Server, ODS folder, Excel, SMTP Server | 4 | Robot will extract the report from Putty and forward it to the ODS folder using FTP Server.
QAD_Download_Reports | Putty, 32prn, FTP Server, ODS folder, Excel, SMTP Server | 15 | Robot will extract the reports from Putty and forward it to the ODS folder using FTP Server.
QAD_Inventory_Report | Putty, 32prn, FTP Server, ODS folder, Excel, SMTP Server | 6 | Robot will extract reports from Putty, send mail to customers, and forward it to the FTP server.
ODS_TG1_ExchangeRate |  | Not required | Robot will extract currency data from SAP and enter it into Putty.
QAD_Coater_ODS | Putty, 32prn, FTP Server, ODS folder, Excel, SMTP Server | 6 | Robot will extract reports from Putty, send mail to customers, and forward it to the FTP server.
supplier_master_report | Putty, CMD, Sharepoint, API call, Excel, Database | Automation not required | Robot will extract reports from Putty, send mail to customers, and forward it to the FTP server.
Trading_Grid_Report | Trading frid site, Web beowser(Chrome), UI Interfaces, XML, FTP server, ODS folder, SMTP Server | No Change Required | Robot will extract report from trading site and forward it to FTP server.
User Access Audit Report_7Days | Putty, 32prn, Excel, SMTP Server | 4 | Robot will extract user access detail from Putty, filter it according to business needs and compare with 7 days old user access report, send reminder mail to the users, and send a report to Regina.
User Access Audit Report_14Days | Putty, 32prn, Excel, SMTP Server | 16 | Robot will extract user access detail from Putty, filter it according to business needs and compare with a 14-day-old user access report, and deactivate the user from Putty and send mail to the user and send a report to Regina.
User Access Audit Report | Putty, 32prn, Excel, SMTP Server | 6 | Robot will extract user access detail from Putty, filter it according to business needs, send mail to the users, and send a report to Regina.
Sales For Customer Forecast Report | Putty, 32prn, FTP Server, ODS folder, Excel, SMTP Server | 4 | Robot will extract reports from Putty, send mail to customers, and forward it to the FTP server.
Alyudene Demand Report | Alyudene site, Web beowser(Chrome), UI Interfaces, XML, FTP server, ODS folder, SMTP Server | 8 | Robot will extract the report from Putty and forward it to the ODS folder using FTP Server.
Ereq_QAD_IntegrationAttended | Putty, Sharepoint, API call, Database server, SMTP server, Utility | 0 (No Change Required) | Robot will read data from Sharepoint and enter it into the utility application for the creation of a request ID in the Sharepoint list. Robot will read Sharepoint PO creation list with status "Ready for Creation" and extract all EREQ details and enter them into Putty for PO creation. Once it is done, the robot will update the PO number and date in the SharePoint list and update the database. In case of failure, it will update the EREQs with a PO not generated status and drop mail to the SharePoint team with a failure reason and update the database.
QAD_TIL_Production_Count_Updation | Putty, 10in6 database, Excel, SMTP Server | 40 | The robot will read the 10in6 database and enter the production count into Putty. Robot will update the database with success and failure status and share the exception list with the client.
QAD_Production_Count_Updation | Putty, 10in6 database, Excel, SMTP Server | 5 | The robot will read the 10in6 database and enter the production count into Putty. Robot will update the database with success and failure status and share the exception list with the client.
InterPlant Return Report Process | Putty, 32prn, Excel, SMTP Server | 4 | Robot will extract reports from Putty, send mail to customers.
Past Period Inventory Reports | Putty, 32prn, Excel, SMTP Server | 4 | Robot will extract reports from Putty, send mail to customers.
AutoDesk License Usage Process | Autodesk site, Web beowser(Chrome), UI Interfaces, Excel, FTP server, ODS folder, SMTP Server | 0 (No Change Required) | Robot will extract the license usage report from the Autodesk site and forward it to the FTP server.